## Sheet1
TASK NUMBER | Name of the Task | Date Started | Date Fisnished
1 | Task 1: Define MotorPH's Requirements | 2024-01-15 12:00 | 2024-01-21 18:38 | Done
2 | Task 2: Create your Use Case Diagram | 2024-01-22 12:00 | 2024-02-11 10:04 | Done
3 | Task 3: Create your Wireframes | 2024-01-22 12:00 | 2024-01-25 18:06 | Done
4 | Task 4: Create an Effort Estimate |  |  | Done
6 | Task 5: Create a Project Plan | 2024-01-29 12:00 | 2024-02-03 06:39 | Done
7 | Task 6: Structure your Code |  |  | Done
8 | Task 7: Use the Correct Data Type |  |  | Done
9 | Milestone 1: Requirements Identification Submission | 2024-02-05 12:00 | 2024-02-11 10:41 | Done
11 | Task 8: Calculate Hours Worked |  |  | Done
12 | Task 9: Apply Government Deductions |  |  | Done
13 | Task 10: Read Input from a Text File |  |  | Done
14 | Task 11: Commit your Code to Github |  |  | Done
15 | Milestone 2: Initial Code Submission | 2024-03-04 12:00 | 2024-03-19 11:43 | Done
16 | Task 12: Conduct Quality Assurance
17 | Terminal Assessment: Final Code Submission | 2024-03-25 23:59
18
19
21
22
23
24
25
26
27
28
29
30
31
32
33